## Product Backlog
SIGMA PRODUCT BACKLOG
Central Luzon State University - Scholarship Information and Grants Management Analytics
ID | Epic | Role | User Story | Priority | Story Points | Target Sprint | Current Status | Acceptance Criteria | Current Website Evidence
SIG-01 | Centralized Data Management | Administrative Aide & Head of Scholarship Dept | As an administrator, I want scholarship information stored in one centralized database, so that records are unified and consistently maintained. | High | 8 | Sprint 1 | Done | Student, scholarship, assignment, and history data use the centralized Supabase schema. | Dashboard; Student Records; Scholarships; Supabase migrations
SIG-02 | Data Migration | Administrative Aide & Head of Scholarship Dept | As an administrator, I want historical paper and spreadsheet records digitized, so that previous scholarship history remains searchable. | High | 8 | Sprint 1 | CSV/XLSX import accepts valid historical records; previous terms remain searchable and are not deleted. | Student Records > Import Students; scholarship history
SIG-03 | Record Retrieval | Administrative Aide | As an administrative aide, I want to retrieve records directly from the database, so that I no longer search separate spreadsheets. | High | 5 | Sprint 1 | Records load from the live database and can be opened from Student Records and Scholarships. | Student Records; Scholarships
SIG-04 | Individual Entry | Administrative Aide | As an administrative aide, I want to add one student manually, so that a file import is unnecessary for individual records. | High | 5 | Sprint 1 | Add Student validates required data and unique Student ID, saves the record, and refreshes the table. | Student Records > Add Student
SIG-05 | Duplicate Prevention | Administrative Aide & Head of Scholarship Dept | As an administrator, I want true logical duplicates detected automatically, so that data quality is protected without flagging legitimate multiple scholarships. | High | 8 | Sprint 2 | Duplicate identity uses Student + Scholarship + Academic Year + Semester; different scholarships are not duplicates. | Automatic database trigger; Dashboard Data Review; Reports review modal
SIG-06 | Import Safety | Administrative Aide | As an administrative aide, I want repeated imports handled safely, so that existing records are skipped and valid new records are added. | High | 8 | Sprint 2 | Import preview classifies new, existing, and invalid rows; existing logical records are not overwritten. | Student Records > Import Students preview
SIG-07 | Search | Administrative Aide & Head of Scholarship Dept | As an administrator, I want to search by student name or ID, so that I can find a record immediately. | High | 3 | Sprint 2 | Name and Student ID searches return matching database records and an accurate result count. | Student Records search
SIG-08 | Filtering | Administrative Aide & Head of Scholarship Dept | As an administrator, I want multi-field filters, so that I can narrow records by college, program, scholarship, term, and status. | Medium | 5 | Sprint 2 | Filters work independently and together with search without changing the underlying records. | Student Records filters; Reports & Analytics toolbar
SIG-09 | Scholarship Status | Administrative Aide & Head of Scholarship Dept | As an administrator, I want scholarship and enrollment statuses managed separately, so that Active + Not Enrolled remains valid. | High | 5 | Sprint 3 | Enrollment never automatically expires or deletes a scholarship; status badges clearly separate both concepts. | Student Records; Student Detail; migrations 0020-0022
SIG-10 | Expiration Monitoring | Head of Scholarship Dept | As the department head, I want expiration based on actual end dates, so that renewals are handled on time. | High | 5 | Sprint 3 | Expiring Soon uses the 30-day threshold; Expired uses a passed end date; historical records remain. | Dashboard; Scholarships; daily expiration function
SIG-11 | Enrollment Verification | Administrative Aide | As an administrative aide, I want to preview official enrollment reconciliation, so that bulk changes are safe and understandable. | High | 8 | Sprint 3 | Preview separates matches and non-matches; default changes only matches; Not Enrolled requires explicit complete-list confirmation. | Student Records > Verify Enrollment; migration 0022
SIG-12 | Notifications & Audit | Administrative Aide & Head of Scholarship Dept | As an administrator, I want notifications and an audit trail, so that important changes and responsible admins are traceable. | High | 5 | Sprint 3 | Activity records include actor, time, action, and affected context; notifications link to relevant review areas. | Notification bell; Recent Activity; Activity Log
SIG-13 | Cloud Deployment | Head of Scholarship Dept | As the department head, I want a cloud-hosted system, so that authorized staff can access it beyond one office computer. | High | 5 | Sprint 4 | Authenticated application is available over HTTPS and protected pages validate the Supabase session. | Vercel production deployment; Supabase Auth
SIG-14 | Usability & Responsive UI | Administrative Aide & Head of Scholarship Dept | As an administrator, I want a clear responsive interface, so that routine work is possible on desktop and laptop without advanced skills. | High | 5 | Sprint 4 | Navigation, forms, tables, dialogs, and toolbars remain understandable and responsive. | Dashboard; Student Records; Scholarships; Reports
SIG-15 | Maintainability | System Administrator | As a system administrator, I want modular and documented code, so that future developers can maintain and migrate the system. | Medium | 5 | Sprint 4 | Application modules, migrations, reusable components, and environment examples are organized in source control. | GitHub repository; src; supabase/migrations
SIG-16 | Reports & Analytics | Administrative Aide & Head of Scholarship Dept | As an administrator, I want filterable analytics and PDF export, so that current and historical scholarship information supports decisions. | Medium | 8 | Sprint 4 | Seven report filters update charts and totals; PDF export uses selected filters; historical records remain available. | Reports & Analytics
SIG-17 | SIGMAI Assistant | Administrative Aide & Head of Scholarship Dept | As an administrator, I want a data-grounded assistant, so that I can ask scholarship questions in plain language. | Medium | 8 | Sprint 4 | Answers use live filtered SIGMA data, identify ambiguity, and do not invent students or totals. | SIGMAI chat button and assistant panel
SIG-18 | Account Security | Administrative Aide & Head of Scholarship Dept | As an authorized administrator, I want secure account and password management, so that administrative access remains protected. | High | 5 | Sprint 1 | No public sign-up is offered; protected routes require a valid session; password changes verify current credentials. | Login; Account Settings; Supabase Auth

## Sprint 1 Backlog
SIGMA SPRINT 1 BACKLOG
Sprint goal: Establish secure centralized data management, historical migration, direct retrieval, individual entry, and authenticated administration.
Sprint | Sprint 1 |  | Metric | Value
Status | Completed |  | Committed items | 5
Capacity (points) | 39 |  | Done points | 31
Committed Points | 31 |  | Completion | 100%
ID | Type | User Story Title | Story Points | Priority | Owner / Workstream | Status | Definition of Done
SIG-01 | User Story | scholarship information stored in one centralized database | 8 | High | Centralized Data Management | Done | Student, scholarship, assignment, and history data use the centralized Supabase schema.
SIG-02 | User Story | historical paper and spreadsheet records digitized | 8 | High | Data Migration | Done | Student Records > Import Students; scholarship history
SIG-03 | User Story | to retrieve records directly from the database | 5 | High | Record Retrieval | Done | Student Records; Scholarships
SIG-04 | User Story | to add one student manually | 5 | High | Individual Entry | Done | Student Records > Add Student
SIG-18 | User Story | secure account and password management | 5 | High | Account Security | Done | Login; Account Settings; Supabase Auth
IMPLEMENTATION TASKS
Task ID | Related Story | Task | Estimated Hours | Notes | Owner / Workstream | Status | Acceptance / Test Result
T-01 | SIG-01 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Centralized Data Management | 16 |  | Centralized Data Management | Done | Dashboard; Student Records; Scholarships; Supabase migrations
T-02 | SIG-02 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Data Migration | 16 |  | Data Migration | Done
T-03 | SIG-03 | Implement and verify: Administrative Aide - Record Retrieval | 10 |  | Record Retrieval | Done
T-04 | SIG-04 | Implement and verify: Administrative Aide - Individual Entry | 10 |  | Individual Entry | Done
T-05 | SIG-18 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Account Security | 10 |  | Account Security | Done

## Sprint 2 Backlog
SIGMA SPRINT 2 BACKLOG
Sprint goal: Protect data quality with accurate duplicate rules, safe additive imports, and fast combined search and filtering.
Sprint | Sprint 2 |  | Metric | Value
Status | Completed |  | Committed items | 4
Capacity (points) | 32 |  | Done points | 24
Committed Points | 24 |  | Completion | 100%
ID | Type | User Story Title | Story Points | Priority | Owner / Workstream | Status | Definition of Done
SIG-05 | User Story | true logical duplicates detected automatically | 8 | High | Duplicate Prevention | Done | Automatic database trigger; Dashboard Data Review; Reports review modal
SIG-06 | User Story | repeated imports handled safely | 8 | High | Import Safety | Done | Student Records > Import Students preview
SIG-07 | User Story | to search by student name or ID | 3 | High | Search | Done | Student Records search
SIG-08 | User Story | multi-field filters | 5 | Medium | Filtering | Done | Student Records filters; Reports & Analytics toolbar
IMPLEMENTATION TASKS
Task ID | Related Story | Task | Estimated Hours | Notes | Owner / Workstream | Status | Acceptance / Test Result
T-01 | SIG-05 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Duplicate Prevention | 16 |  | Duplicate Prevention | Done
T-02 | SIG-06 | Implement and verify: Administrative Aide - Import Safety | 16 |  | Import Safety | Done
T-03 | SIG-07 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Search | 6 |  | Search | Done
T-04 | SIG-08 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Filtering | 10 |  | Filtering | Done

## Sprint 3 Backlog
SIGMA SPRINT 3 BACKLOG
Sprint goal: Separate scholarship lifecycle from enrollment, add safe verification, expiration monitoring, notifications, and auditability.
Sprint | Sprint 3 |  | Metric | Value
Status | Completed |  | Committed items | 4
Capacity (points) | 31 |  | Done points | 23
Committed Points | 23 |  | Completion | 100%
ID | Type | User Story Title | Story Points | Priority | Owner / Workstream | Status | Definition of Done
SIG-09 | User Story | scholarship and enrollment statuses managed separately | 5 | High | Scholarship Status | Done | Student Records; Student Detail; migrations 0020-0022
SIG-10 | User Story | As the department head, I want expiration based on actual end dates | 5 | High | Expiration Monitoring | Done | Dashboard; Scholarships; daily expiration function
SIG-11 | User Story | to preview official enrollment reconciliation | 8 | High | Enrollment Verification | Done | Student Records > Verify Enrollment; migration 0022
SIG-12 | User Story | notifications and an audit trail | 5 | High | Notifications & Audit | Done | Notification bell; Recent Activity; Activity Log
IMPLEMENTATION TASKS
Task ID | Related Story | Task | Estimated Hours | Notes | Owner / Workstream | Status | Acceptance / Test Result
T-01 | SIG-09 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Scholarship Status | 10 |  | Scholarship Status | Done
T-02 | SIG-10 | Implement and verify: Head of Scholarship Dept - Expiration Monitoring | 10 |  | Expiration Monitoring | Done
T-03 | SIG-11 | Implement and verify: Administrative Aide - Enrollment Verification | 16 |  | Enrollment Verification | Done
T-04 | SIG-12 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Notifications & Audit | 10 |  | Notifications & Audit | Done

## Sprint 4 Backlog
SIGMA SPRINT 4 BACKLOG
Sprint goal: Complete deployment readiness, responsive usability, maintainability, analytics, and the data-grounded SIGMAI assistant.
Sprint | Sprint 4 |  | Metric | Value
Status | Completed |  | Committed items | 5
Capacity (points) | 39 |  | Done points | 31
Committed Points | 31 |  | Completion | 100%
ID | Type | User Story Title | Story Points | Priority | Owner / Workstream | Status | Definition of Done
SIG-13 | User Story | As the department head, I want a cloud-hosted system | 5 | High | Cloud Deployment | Done | Vercel production deployment; Supabase Auth
SIG-14 | User Story | a clear responsive interface | 5 | High | Usability & Responsive UI | Done | Dashboard; Student Records; Scholarships; Reports
SIG-15 | User Story | modular and documented code | 5 | Medium | Maintainability | Done | GitHub repository; src; supabase/migrations
SIG-16 | User Story | filterable analytics and PDF export | 8 | Medium | Reports & Analytics | Done | Reports & Analytics
SIG-17 | User Story | a data-grounded assistant | 8 | Medium | SIGMAI Assistant | Done | SIGMAI chat button and assistant panel
IMPLEMENTATION TASKS
Task ID | Related Story | Task | Estimated Hours | Notes | Owner / Workstream | Status | Acceptance / Test Result
T-01 | SIG-13 | Implement and verify: Head of Scholarship Dept - Cloud Deployment | 10 |  | Cloud Deployment | Done
T-02 | SIG-14 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Usability & Responsive UI | 10 |  | Usability & Responsive UI | Done
T-03 | SIG-15 | Implement and verify: System Administrator - Maintainability | 10 |  | Maintainability | Done
T-04 | SIG-16 | Implement and verify: Administrative Aide & Head of Scholarship Dept - Reports & Analytics | 16 |  | Reports & Analytics | Done
T-05 | SIG-17 | Implement and verify: Administrative Aide & Head of Scholarship Dept - SIGMAI Assistant | 16 |  | SIGMAI Assistant | Done

## Summary
SIGMA BACKLOG SUMMARY
KPI | Value | Sprint | Items | Story Points
Total backlog items | 18 | Sprint 1 | 5 | 31
Total story points | 109 | Sprint 2 | 4 | 24
Implemented items | 18 | Sprint 3 | 4 | 23
In progress items | 0 | Sprint 4 | 5 | 31
Not started items | 0
Scope Notes
- Backlog content is based on SIGMA requirements, implemented modules, database migrations, and the professor-verification navigation guide.
- Sprint dates and individual assignees should be filled in by the team if required by the instructor.
- Statuses describe the current implemented application as of September 2026.
- Product and sprint estimates are planning values and may be adjusted during team review.

## Website Coverage
SIGMA WEBSITE COVERAGE & TRACEABILITY
Area | Representative Page / Component | Covered Stories | Verification Note
Authentication | Login, Account Settings, AuthProvider | SIG-13, SIG-18 | Admin-only authentication, protected routes, persistent session, password recovery and secure password change.
Student management | Student Records, Add Student, Import Students | SIG-01, SIG-02, SIG-03, SIG-04, SIG-06 | Individual and bulk workflows use the same centralized student and scholarship-assignment schema.
Search and filtering | Student Records search and filter toolbar | SIG-07, SIG-08 | Search and filters combine while preserving accurate result counts.
Duplicate review | Database trigger, Dashboard Data Review, Reports modal | SIG-05 | Logical duplicate identity includes student, scholarship, academic year, and semester.
Enrollment | Verify Enrollment modal and RPC | SIG-09, SIG-11 | Read-only preview and explicit reconciliation confirmation keep enrollment separate from scholarship status.
Scholarship lifecycle | Scholarships, expiration trigger and scheduled refresh | SIG-09, SIG-10 | Actual end dates determine Expiring Soon and Expired without deleting history.
Audit and notifications | Notification bell, Recent Activity, Activity Log | SIG-12 | Administrative actions retain actor and timestamp context.
Analytics | Dashboard and Reports & Analytics | SIG-16 | Database-driven totals, filters, charts, historical comparison, and PDF export.
AI assistance | SIGMAI assistant | SIG-17 | Plain-language questions use live SIGMA data and explicit filters.
Deployment and maintenance | Vercel, Supabase, GitHub repository | SIG-13, SIG-15 | Cloud deployment and versioned migrations support continued operation and maintenance.
Responsive experience | Shared responsive components and horizontal table/toolbars | SIG-14 | Primary workflows support desktop and laptop, with safe narrow-screen overflow or stacking.